## AggieHonorCoder Roadmap
Man-Hours Spent
Task | Priority | Iteration | Owner | Status | Notes
Setup
Manage DB fields neccesary for users/posts | Very High | 2 | All | IP
Markup Sketch | Very High | 1 | Paul | Done |  | 1
Flutter Setup | Very High | 1 | Hayden | Done |  | 2
Login
Access Facebook API | High | 1 | Tommy | Done |  | 1
Create Google API Keys | High | 1 | Chris | Done
Front End Login Page | High | 1 | Hayden/Rob | Done |  | 4
Login with Google | High | 1 | Chris | Done
Login with FB | High | 1 | Tommy | Done |  | 6
User Validation | High | 1 | Tommy/Chris | Done |  | 1
Cucumber/Automated Test Cases | Very High | 1 | Elvis | Done |  | 8
Google stay logged in until signed out | Very High | 2 | Hayden | Done |  | 1
Facebook stay logged in until signed out | Very High | 3 | Tommy | Done |  | 5
Bug: App remembers you even if you sign out when you relaunch app | Medium | 4 | Tommy | Done |  | 1
Facebook release key hash | Very High | 4 | Tommy | NS
BUG: sometimes kicks you out and then you have to sign out before you login. Make it sign you out on login page or something | Very High | 4 | Tommy | Done |  | 1
Animated backgrounds | Low | 4 | Tommy | Done |  | 1
BUG: Sign out signs you back in automatically | Low | 4 | Tommy | Done |  | 0
HomePage/Navbar
Home Page Feed API (backend) show most recent post, ideally scrollable | Very High | 2 | Chris | DONE
Global top bar UI (back, app title, sign out) -we will add to every page but login | High | 2 | Chris | DONE
Global bottom UI bar (feed, new post, profile) - we will add to all pages but login | High | 2 | Chris | DONE |  | 2
Gherkin Testing | Very High | 2 | Elvis | Done |  | 6
Make feed sorted by date | Low | 3 | Rob | done |  | 2
Make scrolling/loading smooth | Medium | 3 | Rob | done |  | 1
Pull down at top to refresh feed | Medium | 3 | Rob | done |  | 1
Load X (~50) posts then load more when you reach the bottom | Medium | 3 | Rob | done |  | 4
Create a feed of recent posts | Very High | 3 | Rob | done |  | 5
Swipe through all posts and rate them (and store info in db) | Very High | 3 | Rob | done |  | 2
Modularize gloabl top/bottom UI (too much duplicated code, make its own widget in own file) | Very High | 3 | Chris | DONE
Make sure global UI is on every page and functional | Very High | 3 | Chris | DONE
Navigation rework to not use push replacement named (push/pop context) | Very High | 4 | Chris | DONE |  | 10
Show a default message telling you to follow people if your feed is empty or you only follow yourself | Very High | 4 | Chris | DONE |  | 1
Make images on login screen load faster (one is black on startup for some reason) | Low | 4 | Chris | DONE
Loading icons are huge on feed, make them small circle loaders | High | 4 | Rob | DONE
Make posts on login screen show the top rated posts (maybe just most recent for now) from feed in last 24 hours | Medium | 4 | someone | DONE
Make new post tab on bottom nav bar work same as home and profile and change order so home is in middle | High | 4 | Chris | DONE |  | 2
Center WooLaLa in top header bar and standardize that | High | 4 | Chris | DONE |  | 1
Make everything use primary swatch | High | 4 | Chris | IP
Fix signout Icon to not be an X | Very High | 4 | Chris | DONE |  | 1
When on search screen highlight nothing in bottom bar | High | 4 | Chris | DONE |  | 1
Make transition animations only play on the interior content (not the top/bottom bars) | Medium | 4 | Chris | NS
most recent post doesnt show until refresh(large blank space in feed before then) | High | 4 | Rob | Done |  | 1
BUG: Back button on feed sends you to old versions of feed (maybe just remove back button in top left) | Very High | 4 | Chris | DONE |  | 2
Change app name to WooLaLa not woolala-app | Very High | 4 | Chris | DONE |  | 2020-01-02
Make app icon the orange W or something | Very High | 4 | Chris | DONE |  | 1
Store posts in cache for faster loading | High | 4 | Chris | NS
Fix icon colors on nav bar using primary swatch, make them highlight correctly | Very High | 4 | Chris | IP |  | 2
Posts
Post creation screen | Very High | 2 | Tommy | Done |  | 2
Upload photo | Very High | 2 | Tommy | Done |  | 2
Take photo | Medium | 2 | Tommy | Done |  | 2
Caption a post | Medium | 2 | Tommy | Done |  | 1
Submit Post to feeds | Very High | 2 | Rob | Done |  | 6
Visual Rating System (Frontend) | Very High | 2 | Rob | Done |  | 2
Rating System (Backend) | Very High | 2 | Rob | Done |  | 4
Gherkin Testing | Very High | 2 | Elvis | Done |  | 6
Post UI design (i.e. instagram post layout) make it look better | Very High | 4 | Hayden | Done |  | 3
Crop pictures | High | 3 | Tommy | Done |  | 3
Make sure all images fill up the screen when in the feed | High | 3 | Tommy | Done |  | 1
Add post id (user id + time base 64 encoded) | Very High | 3 | Rob | done |  | 2
Fix two posts one minute bug | High | 4 | Rob | Done |  | 0.008
Add post to user after posting | Very High | 3 | Rob | done |  | 1
Fix image upload with camera | High | 3 | Rob | done |  | 1
Display user profile on post/ rework feed to include users | High | 3 | Rob | done |  | 2
Fix Captions - users can enter down a lot (we need to cap them out at 3 lines regardless) | Very High | 4 | Tommy | Done |  | 1
Swipe score like Tito wants from anywhere on screen | Very High | 4 | Rob | Done |  | 5
Add date to post | High | 4 | Rob | Done |  | 1
Add I would buy this to posts (shopping cart icon) | Very High | 4 | Hayden | Done |  | 1
Watermark post for sharing | Very High | 4 | Hayden | Done |  | 7
Share post to FB | Very High | 4 | Hayden | Done |  | 10
Clicking profile photo on post takes you to their account page | Medium | 4 | Hayden | Done |  | 1
Show apost average rating on post after you rate | High | 4 | Rob | Done |  | 2
Only Rate a post one time | Very High | 4 | Rob | Done |  | 8
Fix error if you back out of image selection | Low | 4 | Tommy | Done |  | 1
Click i would buy and change Icon to show you clicked it already | Very High | 4 | Tommy | Done |  | 1
See who clicked I would buy on your own post like viewing your followers in your profile | Very High | 4 | Tommy | Done |  | 5
Image Crop makes app bar text grey | Medium | 4 | Tommy | Done |  | 100
Report a post | Medium | 4 | Hayden | Done |  | 4
Three dots on the right hand side above post | Medium | 4 | Rob | Done |  | 1
Limit caption length to 2-3 lines max (then adjust size box to fit that as tightly as possible if you dont have time for the above task^) | Very High | 4 | Tommy | Done |  | 1
Post background is light grey - make it white (notice contrast in post and account above post) | Low | 4 | Tommy | Done |  | 1
Bug: images too small | Medium | 4 | Tommy | Done |  | 1
Image Filters | Low | 4 | Unassigned | NS
Profile
User Profile (Front end UI) | High | 2 | Hayden | Done |  | 2
Keep track of who is signed in | Very High | 2 | Hayden | Done |  | 1
Display profile info from google/fb account | Low | 2 | Hayden | Done |  | 2
Edit profile details UI | Low | 2 | Hayden | Done |  | 1
Store user accounts in database | High | 2 | Hayden | Done |  | 2
Show profile photos or default photo | High | 3 | Hayden | Done |  | 3
Edit bio | Medium | 3 | Hayden | Done |  | 2
Edit profile name | Medium | 3 | Hayden | Done |  | 2
Add support for 1.2k, 2.3M etc | Medium | 3 | Hayden | Done |  | 1
Dynamic profile stats (followers, posts, rated, avg. rating) | High | 3 | Hayden | Done |  | 4
Edit @username | High | 3 | Hayden | Done |  | 1
Unique Username check upon account creation | High | 3 | Hayden | Done |  | 2
Edit profile pic | High | 4 | Hayden | Done |  | 7
Public/Private accounts | Low | 3 | Hayden | Done |  | 1
Gherkin Testing (Edit bio, show posts, public/private account) | High | 3 | Elvis | Done |  | 6
Delete your account from edit profile page (update follower/following lists) | High | 4 | Paul | Done |  | 6
Change delete account function so it's one button that says "Delete Account" at bottom of edit profile screen | High | 4 | Paul | Done |  | 2
Show your posts beneath profile like instagram | Medium | 4 | Tommy | Done |  | 6
Bug: trim out non alphanumeric characters from @username and spaces before changing it | High | 4 | Hayden | Done |  | 1
Delete a post you made from your account page | Medium | 4 | Rob | Done |  | 1
Fix seeing own posts in profile pages | Very High | 4 | Tommy | Done |  | 1
On someone else's profile page, if you click profile button wont go back to your profile, just stays where its at | High | 4 | Chris | DONE |  | 1
Bug: make sure profile card has updated functionality of most recent version of feed card | High | 4 | Tommy | Done |  | 1
Bug: User profile feed broken on other user's profile pages | High | 4 | Tommy | Done |  | 1
Bug: Top user part is scrollable when only the whole feed should be scrollable | High | 4 | Tommy | Done |  | 1
Bug: fix seeing own feed on someone elses profile | High | 4 | Tommy | Done |  | 1
Followers
Search profiles UI | High | 2 | Paul | Done |  | 10
When accont is deleted userID needs to be removed from other users followers and following lists | Medium | 4 | Paul | Done |  | 1
Recognize if the profile page belongs to you or someone else | Very High | 3 | Paul | Done |  | 2
Recognize if you are already following this account | High | 3 | Paul | Done |  | 2
Give User a list of followers | Very High | 3 | Paul | Done |  | 1
View a list of your followers on account page | Medium | 3 | Paul | Done |  | 2
Search profiles to add followers (go to followers account page and click follow) | Very High | 3 | Paul | Done |  | 6
Gherkin Testing | High | 3 | Elvis | Done |  | 6
Add - or x to stop following someone in following list | High | 4 | Paul | Done |  | 4
Can't see/unfollow your own account in following/search list | Very High | 4 | Paul | Done |  | 4
Follow accounts | Very High | 4 | Rob | Done |  | 4
Follow button update text (follow back, requested, request) | Medium | 4 | Paul | Done |  | 3
Remove followers | High | 4 | Paul | Done |  | 2
Server Side
Setup express API | Very High | 2 | Rob | Done |  | 2
Privatize repo information | Very High | 2 | Elvis | Done |  | 1
Change readme | Very High | 2 | Elvis | Done |  | 1
Find a secure way to save all our account passwords and share with us | Very High | 2 | Elvis | Done |  | 1
API to update users | Very High | 3 | Hayden | Done |  | 2
Images in DB (to and fro) | Very High | 3 | Rob | DONE |  | 4
Push Notifications
Someone wants to buy your post | Medium | 4 | Elvis | IP
Someone rated your post | Medium | 4 | Elvis | IP
Someone started following you | Medium | 4 | Elvis | IP |  | 21
Search
BUG: search for a user then type incorrect letter then delete it and users dont pop up in feed | High | 4 | Paul | Done |  | 1
Search by hashtags on posts | Low | 4 | Paul | NS |  | 1
Deploying
Look into getting woolala on ios/android app store / get us ready to deploy by end of iteration 4 | Medium | 3 | Elvis | NS |  | 0
Deploy server to aws/heroku | Medium | 4 | Rob | Done |  | 3
Deploy app to playStore and TestFlight | Very High | 4 | Hayden | IP |  | 1
Make dev accounts for app launch | Very High | 4 | Tito | Done |  | 1
Clean up your code | Very High | 4 | Everyone | IP
Fulfill Apple's request to qualify from TestFlight to AppStore

## Documentation
Account master email | fashionxtllc@gmail.com | Pswd: Fash10nxt*7
Coding Tool used: Flutter
AWS: | fashionxt@gmail.com | Pswd: Fash10nxt*7

## Old Roadmap
Item-name | iOS | Android | Status (DONE, IP, NS) | Comment |  | ETA -IOS |  | ETA-Android
Item Headline |  |  |  |  | October | November | December | October | November | December
Connect through FB | Login | Login
Connect through Google | Login | Login
Connect to Social Media 1 | NS | NS |  | Share to other services |  |  | 10 |  | 5
Connect to Social Medai 2 | NS | NS |  | Share to other services |  |  | 10 |  | 5
Item Headline: | Opening Screen for Account Holder. (note: it's not mandatory for user to score to be able to go to next image)
Home Page Feed (iOS) | IP | [5 empty] | 5
Home Page Feed (Android) |  | IP |  | Need to update UI |  |  |  |  | IP/10
Initial Friend Request | Done | IP |  | Need to make fake accounts |  |  |  |  | IP/10
Item Headline: | Self-Image Upload
Upload | Done | Done (need to implement) |  | Uploading works |  |  |  |  | IP/10
Crop | NS | Done |  |  |  |  | 8 | Done
Filter?? | NS | NS |  |  |  |  | 8 |  | 12
Caption | Done | IP
Post | Done | IP | [6 empty] | IP/7
Delete posted image | NS | NS |  |  |  |  | 5
Item Headline: | Self-Image Share to other social media
Facebook | NS | NS |  | Post to service |  |  | 9 |  | 10
Twitter | NS | NS |  | Post to service |  |  | 9 |  | 10
Item Headline: | Edit Profile Page (editable texts -- self info, pswd etc)
Username | IP | NS |  |  |  |  | 6 |  | 12
Self Info | IP | IP |  |  |  |  | 6 |  | 12
Location | IP | NS |  |  |  |  | 6 |  | 10
Item Headline: | Self Main Page (observing self images, profile)
View images posted | NS | NS |  |  |  |  | 7 |  | 10
Item Headline: | Others' Pages (viewing images+score, profile)
Searching Profiles | NS | [5 empty] | 8 |  | 10
Viewing Profiles | NS | [5 empty] | 8 |  | 10
Item Headline: | Rate Other's images by sliding
Rate with slides and register | IP | IP (needs to implement in backend) |  |  |  |  | 5 |  | 12/IP
Editing scores | NS | NS |  |  |  |  | 5